***Sub Engineer***

1. Which one of the following represents an activity

a. curing of concrete

b. setting of question paper

c. preparation of breakfast

d. all the above.

Explanation: Option D is correct.

Activity means a consume resources & And has a Definite beginning & end.
The beginning & Completion of an activity.

2. Pick up the incorrect statement from the following:

a. The tail of the arrow indicates the start of the activity

b. The head of the arrow indicates the end of the activity

c. The arrows are drawn to scale from left to right

d. Each activity consumes a given time.

Explanation: Option C is correct.

There is no significance of the length of the arrow in the project network.
It can be drawn from left to right or right to left.

3. The technique for establishing and maintaining priorities among the various jobs of a project, is known

a. Event flow scheduling technique

b. Critical ratio scheduling

c. Slotting technique for scheduling

d. Short interval scheduling.

Explanation: Option B is correct.

Critical in the sense that activities under this path are the priorities and cannot be delayed. The delay of any of the activities in this path is directly delay the whole project.

4. Mile Stone charts were invented in the year of

a. 1920

b. 1930

c. 1940

d. 1950

Explanation: Option C is correct.

5. Frederick W. Taylor introduced a system of working known as

a. line organisation

b. line and staff organisation

c. functional organisation

d. effective organisation.

Explanation: Option C is correct.

6. If to, tp and tm are the optimistic, pessimistic and most likely time estimates of an activity respectively, the expected time t of the activity will be

a.

b.

c.

d.

Explanation: Option D is correct.

7. In the given figure, the network of a project represents

a. activity of an excavation of a footing

b. activity of an excavation which starts at event No. 1 and ends at even No. 2

c. activity of excavation which takes 8 units of time

d. none of these.

Explanation: Option C is correct.

B is wrong because there is no arrow-head that would tell which is a head event and which is tail event.
A is true but C gives more detail in addition to A.  Thatss why it is preferred over A.

8. Pick up the PERT event from the following:

a. Digging of foundation completed

b. Laying of concrete started

c. Laying of concrete completed

d. All the above.

Explanation: Option D is correct.

PERT means program evaluation revised time. Best eg is any scientific project like ISRO. Which required some time for this project but approximately.

9. If D is the duration, ES and EF are the earliest start and finish, LS and LF are latest start and latest finish time, then the following relation holds good

a. LS = LF - D

b. LF = LS + D

c. D = EF - ES

d. all the above.

Explanation: Option D is correct.

10. Final technical authority of a project lies with

a. Assistant Engineer

b. Executive Engineer

c. Superintending Engineer

d. Chief Engineer.

Explanation: Option D is correct.

11. The performance of a specific task in CPM, is known

a. Dummy

b. Event

c. Activity

d. Contract.

Explanation: Option C is correct.

The beginning and end of a job, are called events.
The performance of the specific task in CPM is called activity.

12. Pick up the correct statement from the following:

a. If the float is positive and the activity is delayed by a period equal to its total float, the completion of project is not delayed

b. If the float of an activity is negative, delay in its performance is bound to delay the completion of project

c. If the float of an activity is zero, the activity is critical and any delay in its performance will delay the whole project

d. All the above.

Explanation: Option D is correct.

Except for critical path, all other network paths have different completion time and if any path has more or less or equal time then the critical path, then that path is called +ve, -ve or =  FLOAT.

13. A Milestone chart

a. shows the interdependencies of various jobs

b. depicts the delay of jobs, if any

c. points outgoing ahead of schedule of jobs, if any

d. none of these.

Explanation: Option D is correct.

In a milestone, chart milestones are generally used to show the completion of different sub-activities and also the progress of a project can be shown.

14. Completion of an activity on CPM network diagram, is generally known

a. Event

b. Node

c. Connector

d. All the above.

Explanation: Option D is correct.

15. A dummy activity

a. is artificially introduced

b. is represented by a dotted line

c. does not consume time

d. all the above.

Explanation: Option D is correct.

A Dummy activity is a type of operation in a project network that neither requires any time nor any resource. It is an imaginary activity shown in a project network to identify the dependence among operations.

16. Military organisation is known as

a. line organisation

b. line and staff organisation

c. functional organisation

d. none of these.

Explanation: Option A is correct.

The line organization order directly flows through the head of the organization to ground level and head of organization make decision signal with out consulting others.

17. Pick up the incorrect statement from the following:

a. The beginning and end of a job, are called events

b. The activity which consumes maximum time, is called a node

c. Logically and sequentially connected activities and events form a network

d. None of these.

Explanation: Option B is correct.

18. Various activities of a project, are shown on bar charts by

a. vertical lines

b. horizontal lines

c. dots

d. crosses.

Explanation: Option B is correct.

First time developed by Henry Gantt around 1900 and is used to deal with complex activities.
The bar chart consists of two coordinates, the horizontal represents the time elapsed and the vertical represents the job or activities performed.

19. Time and progress chart of a construction, is also known as

a. Gantt chart

b. Modified Mile stone chart

c. Critical path method chart

d. All the above.

Explanation: Option D is correct.

20. Critical Path Net Work helps an engineer

a. to concentrate his attention on critical activities

b. to divert the resources from non-critical advanced activities to critical activities

c. to be cautious for avoiding any delay in the critical activities to avoid delay of the whole project

d. all the above.

Explanation: Option D is correct.

21. If a is the optimistic time, b is the pessimistic time and m is most likely time of an activity, the expected time of the activity, is

a.

b.

c.

d.

Explanation: Option C is correct.

22. The time by which activity completion time can be delayed without affecting the start of succeeding activities, is known as

a. duration

b. total flat

c. free float

d. interfering float.

Explanation: Option C is correct.

23. The artificial activity which indicates that an activity following it, cannot be started unless the preceding activity is complete, is known as

a. event

b. free float

c. dummy

d. constant

Explanation: Option C is correct.

24. Henry Gantt developed Bar charts for planning and scheduling of projects in

a. 1900

b. 1920

c. 1940

d. 1950

Explanation: Option A is correct.

25. The most popular type of organisation used for Civil Engineering Constructions, is

a. line organisation

b. line and staff organisation

c. functional organisation

d. effective organisation.

Explanation: Option A is correct.

26. The difference between the time avail-to do a job and the time required to do the job, is known as

a. event

b. float

c. duration

d. constraint.

Explanation: Option B is correct.

Float =Time availed - Time Required.
Float shows the time within which you can delay an activity without affecting the overall duration of a project.

27. The object of technical planning, is

a. preparation of estimates

b. initiating the procurement action of resources

c. taking remedial action for likely bottleneck in the execution

d. all the above.

Explanation: Option D is correct.

28. The salient feature of functional organisation is

a. separation of planning and design part

b. each individual maintains functional efficiency

c. work is properly planned and distributed

d. all the above.

Explanation: Option D is correct.

29. Critical path method

a. provides a realistic approach to daily problems

b. avoids delays which are very common in bar charts

c. was invented by Morgan R. Walker of Dupot and James E. Kalley or Remington U.S.A. in 1957

d. All the above.

Explanation: Option D is correct.

30. CPM is

a. is built of activities oriented programme

b. is based on time estimate

c. is used for repetitive works

d. all the above.

Explanation: Option D is correct.

It should be B.
Expl:repetitive work and time estimate it deals with PERT.
PERT is concerned with research where repetitive works are done and there are three time estimates in this while in CPM there duration is given.

31. Critical path lies along the activities having total float

a. positive

b. negative

c. zero

d. same.

Explanation: Option C is correct.

32. Construction team means

a. an architect

b. an owner

c. a contractor

d. all the above.

Explanation: Option D is correct.

33. Pick up the correct network for the activities of pouring concrete, erection of form work, removal of form work and curing of concrete from the following:

a. 1. Pouring of Concrete  2. Erection of form work 3. Curing of concrete 4. Removal of form work

b. 1. Erection of form work 2. Pouring of concrete 3. Curing of concrete 4. Removal of form work

c. 1. Removal of form work  2. Erection of form work 3. Pouring of concrete 4. Curing of concrete

d. 1. Pouring of concrete 2. Curing of concrete 3. Erection of form work 4. Removal of form work

Explanation: Option B is correct.

It differs as the structure varies.
In Case of slab, removal of formwork is after curing while in column curing is after removal of formwork.

34. A construction schedule is prepared after collecting

a. output of labour

b. output of machinery

c. quantity of various items

d. all the above.

Explanation: Option D is correct.

35. Site order book is used for recording

a. instructions by the executive engineers

b. construction measurements

c. issue of store equipments

d. names of the casual labour.

Explanation: Option A is correct.

70% checking by an AEE.
30% checking by a EE.
What ever instruction or suggestion , it has to be written on that book so that when ever inspection team come further, they can examine the difference between previous and today's work.

36. An Executive Engineer may have powers upto

a. Rs. 25,000

b. Rs. 50,000

c. Rs. 100,000

d. Rs. 200,000

Explanation: Option A is correct.

CE - All powers.
SE - Upto 15 lakhs (Superintending engineer).
EE- Upto 5 Lakhs.
( Source estimation and costing by BN DATTA).

37. The main principle of an organisation, is

a. cohegency

b. effective control at all levels

c. delegation of authority

d. all the above.

Explanation: Option D is correct.

38. The estimated time required to perform an activity, is known as

a. event

b. dummy

c. duration

d. float.

Explanation: Option C is correct.

39. A CPM family includes

a. CPP (Critical Path Plotted)

b. MCE (Minimum Cost Expenditure)

c. CPS (Critical Path Scheduling)

d. All the above.

Explanation: Option D is correct.

40. The time which results in the leasi, possible construction cost of an activity, is known

a. normal time

b. slow time

c. crash time

d. standard time.

Explanation: Option B is correct.

There is no any concept of a slow time for normal time cost is normal cost least cost occurs at the optimum time only.

41. If the total float and duration of an activity are 5 and 10 days respectively, the particular activity can be

a. started 5 days later

b. completed 5 days later

c. performed at slower rate in 15 days

d. all the above.

Explanation: Option D is correct.

42. Works costing less than Rs. 20,000 are treated as

a. projects

b. major projects

c. minor projects

d. all the above.

Explanation: Option C is correct.

Petty work = <2500 /-
Minor Work = 2500-20000 /-
Major Work = 20000-100000 /-
Project = > 1 lac.

43. A critical ratio scheduling

a. determines the status of each activity

b. adjusts automatically changes in activity progress

c. is a dynamic system

d. none of these.

Explanation: Option D is correct.

Critical Ratio Scheduling is the Technique for establishing & maintaining priorities among the various jobs of a project.
Hence option A is correct.

44. Bar charts are suitable for

a. minor works

b. major works

c. large projects

d. all the Above.

Explanation: Option A is correct.

45. The first method invented for planning projects, was

a. Bar chart method

b. Milestone chart

c. Critical path method (CPM)

d. Programme Evaluation and Review Technique (PERT)

Explanation: Option A is correct.

46. If TL is the latest allowable event occurrence time, total activity slack(s), is equal to

a. LST-EST

b. LFT-EFT

c. TL-EFT

d. all the above.

Explanation: Option D is correct.

LST/LAST START TIME.
EST/EARLIEST START TIME.
LFT/LAST FINISH TIME.
EFT/EARLIEST FINISH TIME.

47. The Overall in-charge of an organisation at the site responsible for the execution of the works, is

a. Engineer

b. Junior Engineer

c. Sub overseer

d. Assistant Engineer.

Explanation: Option A is correct.

48. Modular co-ordination of construction means proper

a. planning

b. designing

c. execution

d. all the above.

Explanation: Option D is correct.

49. Pick up the correct statement from the following:

a. PERT analysis is event oriented

b. CPM does not make any allowance for the uncertainties in the duration of time

c. In CPM, the time is related to cost

d. All the above.

Explanation: Option D is correct.

50. If t is the duration of an activity, t1 is the latest finish possible moment of its preceding activity and t2 is the earliest start possible moment, the independent float of the activity is

a. (t1 - t2) - t

b. t - (t1 - t2)

c. (t1 + t2) - t

d. t + (t1 - t2)

Explanation: Option A is correct.

51. Pick up the correct statement from the following:

a. Latest occurrence time is denoted by TL

b. Contractual obligation time is denoted by Ts

c. Latest occurrence time is taken as contractual obligation time

d. All the above.

Explanation: Option D is correct.

52. For the supply of materials for concrete, form work reinforcing and placing of concrete, removal of form work and curing of concrete, number of bar(s) required on bar chart, is

a. 1

b. 2

c. 3

d. 4

Explanation: Option A is correct.

53. For the execution of a project, a contractor is

a. a person

b. a firm

c. an agency

d. all the above.

Explanation: Option D is correct.

A person or firm or an agency that undertakes a contract to provide materials or labour to perform a service or do a job.

54. Railway projects are treated as

a. light construction

b. heavy construction

c. industrial construction

d. none of these.

Explanation: Option B is correct.

Railway construction is heavy project because machines and skilled people are required for assembling the metals to come up with rail path.

55. Pick up the correct statement from the following:

a. Pessimistic time estimate refers to activities

b. Most likely time estimate refers to activities

c. Expected time estimate refers to activities

d. All the above.

Explanation: Option D is correct.

56. The critical activity has

a. maximum float

b. minimum float

c. zero float

d. none of these.

Explanation: Option C is correct.

57. The main disadvantage of line organisation, is

a. rigid structure

b. extraordinary delay in communications

c. top level executions over work

d. all the above.

Explanation: Option D is correct.

58. Pick up the correct statement from the following:

a. The difference of latest occurence time and earliest expected time, is called slack

b. The activities connecting the events having zero slack, lie on the critical path

c. The critical path consumes the maximum time

d. All the above.

Explanation: Option D is correct.

59. Pre-tender stage requires

a. selection of site

b. formalisation of alignment of work

c. formalisation of designs and preparation of estimate

d. all the above.

Explanation: Option D is correct.

60. The final selection of a construction site, is done by

a. local civil authority representative

b. representative of engineer authority

c. representative of administration

d. all the above.

Explanation: Option D is correct.

61. Pick up the correct statement from the following:

a. The duration of time by which an activity can be delayed without affecting the succeeding activity, is called free float

b. The float which affects neither the processor nor the successor activities, is called independent float

c. The difference between total float and free float, is called interfering float

d. All the above.

Explanation: Option D is correct.

62. The first stage of a construction, is

a. survey of the site

b. initiation of proposal

c. preparation of tender

d. allotment of funds.

Explanation: Option B is correct.

It's very necessary to have first of all what kind of construction we have to do then we can go for further process.

63. PERT is

a. limited of event oriented diagrams

b. used for research and development projects

c. based on three time estimates for activities linking up two events

d. all the above.

Explanation: Option D is correct.

64. Residential buildings are treated as

a. light construction

b. heavy construction

c. industrial construction

d. private construction.

Explanation: Option A is correct.

65. The main advantage of line organisation, is :

a. defined responsibilities at all levels

b. rigid discipline in the organisation

c. ability of quick decision at all levels

d. all the above.

Explanation: Option D is correct.

66. PERT analysis is based on

a. optimistic time

b. pessimistic time

c. most likely time

d. all the above.

Explanation: Option D is correct.

67. For completion of a project, the critical path of the network represents

a. minimum time

b. maximum time

c. maximum cost

d. minimum cost.

Explanation: Option A is correct.

The critical path is longest path consumes max time and resources so option B is correct.
Source khurmi book.

68. In CPM analysis,

a. uncertainties are not allowed

b. activities are represented by arrows

c. beginning and end of an activity, are denoted by nodes

d. all the above.

Explanation: Option D is correct.

69. A goiden rule for the procurement of construction stones, suggests

a. 67% at the site and 33% under procurement

b. 50% at the site and 50% under procurement

c. 33% at the site and 67% under procurement

d. none of these.

Explanation: Option A is correct.

70% material must be available at site, rest 30% we can procure. If it imbalanced then cost of the project and completion of the project will directly affect.
Its can vary for building construction but the rule must follow in road construction.

70. Power stations are generally treated as

a. light construction

b. heavy construction

c. industrial construction

d. electrical construction.

Explanation: Option C is correct.

Railway -  Heavy Construction.
Residential Building - Light Construction.
Power Station - Industrial Construction.

71. An event is indicated on the network by a number enclosed in

a. a square

b. a triangle

c. an ellipse

d. all the above.

Explanation: Option D is correct.

72. Pick up the incorrect statement from the following:

a. The difference between the maximum time available for the job and actual time it consumes, is called total float

b. The difference between the latest start time and earliest start time of an activity, is called total float

c. The difference between the earliest finish time of an activity and the earliest start time of its successor activity, is called free float of the activity

d. None of these.

Explanation: Option D is correct.

Actually, option D is wrong because in the case of free float it is the maximum time that can be delayed without affecting the start of the successor activity.
Thus it is Est of successor-Est of predecessor-duration.

73. While scheduling a project by C.P.M.

a. required time for each activity is established

b. sequence of various activities is made according to their importance

c. net work is drawn by connecting the activities and the events

d. All the above.

Explanation: Option D is correct.

74. Pick up the correct statement from the following with regards to C.P.M. network analysis of projects

a. Earliest occurrence time of the event from which the activity arrow originates plus the duration of the activity, is called earliest finish time of the activity

b. The latest occurrence time of the node of which the activity arrow terminates minus the duration of the activity, is called latest start time

c. The latest occurrence time for the node at which the activity arrow terminates, is called latest finish time

d. All the above.

Explanation: Option D is correct.

75. Pick up the correct statement from the following:

a. Backward pass is used for calculating the latest occurence time

b. Maximum value of earliest expected time is used if there are more than one value of any event

c. Minimum value of latest occurrence time is used if there are more than one value of any event

d. All the above.

Explanation: Option D is correct.

76. Which one of the following represents an event ?

a. concrete cured

b. fixing of door

c. plastering of walls

d. selecting sites

Explanation: Option A is correct.

So, any action that is in continuation is called activity and that already has been completed is called an event.

77. Pick up the incorrect statement from the following:

a. The various functions under each activity, are shown by one bar on Bar Charts

b. Bar chart establishes the interdependency of one event on another

c. Only approximate percentage of the completed work is reported

d. None of these,

Explanation: Option B is correct.

78. For the network shown in the given figure, the expected time for the activity

a. 1-2 is 4

b. 2-3 is 7

c. 3-4 is 8

d. all the above.

Explanation: Option D is correct.

79. Frequency distribution curves

a. having a single lump, are called uninodal curves

b. if symmetrical, are called normal curves

c. if not symmetrical, are called skew curves

d. all the above.

Explanation: Option D is correct.

80. Pick up the correct statement from the following:

a. Programme Evaluation and Review Technique, is event oriented

b. Programme Evaluation and Review Technique is not event oriented

c. Critical Path Method is event oriented

d. Critical Path method is event oriented.

Explanation: Option A is correct.

PERT :-
Event Oriented.
Probabilistic approach.
Suitable for new project.
1950.
Beta Curve.
CPM :-
Activity oriented.
Deterministic approach.
Suitable for repetative work.
1957.
Normal distribution curve.

81. The three time estimates for the activities of the network shown in the given figure are shown above their arrows. The earliest expected time for the event 4, is

a. 19

b. 14

c. 24

d. None of these.

Explanation: Option A is correct.

Using PERT formula for each activity. Add the value obtained to get 19.
Activity 1-2  => (3+(4*4)+5)/6 = 4.
2-3 =>(5+(7*4)+9)/6 = 7.
3-4 => (6+(4*4)+10)/6 = 8.
4+7+8 = 19.

82. Optimistic time, most likely time and pessimistic times for the activities of a network in the given figure are written above their arrows. If the contractual obligation time for the project is 75, the latest occurrence time for the event 2, is

a. 20

b. 25

c. 35

d. 15

Explanation: Option B is correct.

For latest occurence time, backward pass method is used and for earliest expected time, forward pass method is used.

83. While filling the tender for any work, the contractor considers

a. availability of construction materials

b. availability of labour

c. study of specifications

d. all the above.

Explanation: Option D is correct.