***Sub Engineer***

1. Which one of the following represents an activity

a. curing of concrete

b. setting of question paper

c. preparation of breakfast

d. all the above.

2. Pick up the incorrect statement from the following:

a. The tail of the arrow indicates the start of the activity

b. The head of the arrow indicates the end of the activity

c. The arrows are drawn to scale from left to right

d. Each activity consumes a given time.

3. The technique for establishing and maintaining priorities among the various jobs of a project, is known

a. Event flow scheduling technique

b. Critical ratio scheduling

c. Slotting technique for scheduling

d. Short interval scheduling.

4. Mile Stone charts were invented in the year of

a. 1920

b. 1930

c. 1940

d. 1950

5. Frederick W. Taylor introduced a system of working known as

a. line organisation

b. line and staff organisation

c. functional organisation

d. effective organisation.

6. If to, tp and tm are the optimistic, pessimistic and most likely time estimates of an activity respectively, the expected time t of the activity will be

a.

b.

c.

d.

7. In the given figure, the network of a project represents

a. activity of an excavation of a footing

b. activity of an excavation which starts at event No. 1 and ends at even No. 2

c. activity of excavation which takes 8 units of time

d. none of these.

8. Pick up the PERT event from the following:

a. Digging of foundation completed

b. Laying of concrete started

c. Laying of concrete completed

d. All the above.

9. If D is the duration, ES and EF are the earliest start and finish, LS and LF are latest start and latest finish time, then the following relation holds good

a. LS = LF - D

b. LF = LS + D

c. D = EF - ES

d. all the above.

10. Final technical authority of a project lies with

a. Assistant Engineer

b. Executive Engineer

c. Superintending Engineer

d. Chief Engineer.

11. The performance of a specific task in CPM, is known

a. Dummy

b. Event

c. Activity

d. Contract.

12. Pick up the correct statement from the following:

a. If the float is positive and the activity is delayed by a period equal to its total float, the completion of project is not delayed

b. If the float of an activity is negative, delay in its performance is bound to delay the completion of project

c. If the float of an activity is zero, the activity is critical and any delay in its performance will delay the whole project

d. All the above.

13. A Milestone chart

a. shows the interdependencies of various jobs

b. depicts the delay of jobs, if any

c. points outgoing ahead of schedule of jobs, if any

d. none of these.

14. Completion of an activity on CPM network diagram, is generally known

a. Event

b. Node

c. Connector

d. All the above.

15. A dummy activity

a. is artificially introduced

b. is represented by a dotted line

c. does not consume time

d. all the above.

16. Military organisation is known as

a. line organisation

b. line and staff organisation

c. functional organisation

d. none of these.

17. Pick up the incorrect statement from the following:

a. The beginning and end of a job, are called events

b. The activity which consumes maximum time, is called a node

c. Logically and sequentially connected activities and events form a network

d. None of these.

18. Various activities of a project, are shown on bar charts by

a. vertical lines

b. horizontal lines

c. dots

d. crosses.

19. Time and progress chart of a construction, is also known as

a. Gantt chart

b. Modified Mile stone chart

c. Critical path method chart

d. All the above.

20. Critical Path Net Work helps an engineer

a. to concentrate his attention on critical activities

b. to divert the resources from non-critical advanced activities to critical activities

c. to be cautious for avoiding any delay in the critical activities to avoid delay of the whole project

d. all the above.

21. If a is the optimistic time, b is the pessimistic time and m is most likely time of an activity, the expected time of the activity, is

a.

b.

c.

d.

22. The time by which activity completion time can be delayed without affecting the start of succeeding activities, is known as

a. duration

b. total flat

c. free float

d. interfering float.

23. The artificial activity which indicates that an activity following it, cannot be started unless the preceding activity is complete, is known as

a. event

b. free float

c. dummy

d. constant

24. Henry Gantt developed Bar charts for planning and scheduling of projects in

a. 1900

b. 1920

c. 1940

d. 1950

25. The most popular type of organisation used for Civil Engineering Constructions, is

a. line organisation

b. line and staff organisation

c. functional organisation

d. effective organisation.

26. The difference between the time avail-to do a job and the time required to do the job, is known as

a. event

b. float

c. duration

d. constraint.

27. The object of technical planning, is

a. preparation of estimates

b. initiating the procurement action of resources

c. taking remedial action for likely bottleneck in the execution

d. all the above.

28. The salient feature of functional organisation is

a. separation of planning and design part

b. each individual maintains functional efficiency

c. work is properly planned and distributed

d. all the above.

29. Critical path method

a. provides a realistic approach to daily problems

b. avoids delays which are very common in bar charts

c. was invented by Morgan R. Walker of Dupot and James E. Kalley or Remington U.S.A. in 1957

d. All the above.

30. CPM is

a. is built of activities oriented programme

b. is based on time estimate

c. is used for repetitive works

d. all the above.

31. Critical path lies along the activities having total float

a. positive

b. negative

c. zero

d. same.

32. Construction team means

a. an architect

b. an owner

c. a contractor

d. all the above.

33. Pick up the correct network for the activities of pouring concrete, erection of form work, removal of form work and curing of concrete from the following:

a. 1. Pouring of Concrete  2. Erection of form work 3. Curing of concrete 4. Removal of form work

b. 1. Erection of form work 2. Pouring of concrete 3. Curing of concrete 4. Removal of form work

c. 1. Removal of form work  2. Erection of form work 3. Pouring of concrete 4. Curing of concrete

d. 1. Pouring of concrete 2. Curing of concrete 3. Erection of form work 4. Removal of form work

34. A construction schedule is prepared after collecting

a. output of labour

b. output of machinery

c. quantity of various items

d. all the above.

35. Site order book is used for recording

a. instructions by the executive engineers

b. construction measurements

c. issue of store equipments

d. names of the casual labour.

36. An Executive Engineer may have powers upto

a. Rs. 25,000

b. Rs. 50,000

c. Rs. 100,000

d. Rs. 200,000

37. The main principle of an organisation, is

a. cohegency

b. effective control at all levels

c. delegation of authority

d. all the above.

38. The estimated time required to perform an activity, is known as

a. event

b. dummy

c. duration

d. float.

39. A CPM family includes

a. CPP (Critical Path Plotted)

b. MCE (Minimum Cost Expenditure)

c. CPS (Critical Path Scheduling)

d. All the above.

40. The time which results in the leasi, possible construction cost of an activity, is known

a. normal time

b. slow time

c. crash time

d. standard time.

41. If the total float and duration of an activity are 5 and 10 days respectively, the particular activity can be

a. started 5 days later

b. completed 5 days later

c. performed at slower rate in 15 days

d. all the above.

42. Works costing less than Rs. 20,000 are treated as

a. projects

b. major projects

c. minor projects

d. all the above.

43. A critical ratio scheduling

a. determines the status of each activity

b. adjusts automatically changes in activity progress

c. is a dynamic system

d. none of these.

44. Bar charts are suitable for

a. minor works

b. major works

c. large projects

d. all the Above.

45. The first method invented for planning projects, was

a. Bar chart method

b. Milestone chart

c. Critical path method (CPM)

d. Programme Evaluation and Review Technique (PERT)

46. If TL is the latest allowable event occurrence time, total activity slack(s), is equal to

a. LST-EST

b. LFT-EFT

c. TL-EFT

d. all the above.

47. The Overall in-charge of an organisation at the site responsible for the execution of the works, is

a. Engineer

b. Junior Engineer

c. Sub overseer

d. Assistant Engineer.

48. Modular co-ordination of construction means proper

a. planning

b. designing

c. execution

d. all the above.

49. Pick up the correct statement from the following:

a. PERT analysis is event oriented

b. CPM does not make any allowance for the uncertainties in the duration of time

c. In CPM, the time is related to cost

d. All the above.